## Immediate
Entry Date | Tasks | Owner | Target Dt | Status | Comments
2013-04-07 | Follow-up with Sahasra on: - Branding - Pricing - Process - Shipment Process - Legal/Warranty - Arrange for Technical know-how | Ajay |  |  | Technical know how need to be done. Others they are open for discussion and negotiation based on quatity. For branding they need order of atleast 1lac pricing - they have circulated
2013-04-07 | Follow-up with Gaur on: - Priority Item - Pricing - Procurement Process - Courier the Torch - Legal/Warranty - Cetification requirement | Ajay |  |  | Discussed with Gaur on 18th April'13. He is not clear on process of railways. He have circulated specification to different departments. But it seems it can be long process. May be Sahasra or Moxie brand need approval from railways. In continuous follow up with Gaur. For Torch, he didnt have at that time, he will provide during my next visit
2013-04-07 | Branding and its issues | Ajay |  |  | Working on it: first exploring adaptor and lantern/emergency light models. Discussed with various vendors in rajasthan(jaipur, paota and jhunjunu) . Vendors in Dharuhera(haryana) and vendors in areas near greater noida. These people have two type of backup lights 1) Torch light -Shape of torch, but fits in bulb holder. It have battery, when light goes off, its led glows. Very low back up in market at Rs70-Rs150/- 2) CFL/LED based emergency lights, charged through ac. Back-up of 3-4 hours - in market in villages at Rs600 to Rs1200. Higher cost variants normally have some other features like FM, watch etc. Shopkeepers have margins from 50% to 100% so very interested in selling them Open points are 1) process of transport 2) warranty 3) legalities
2013-04-07 | Check IKIO for product catalogue and prices | Sat
2013-04-07 | Check Battery Chargers for Railways | Ajay
2013-04-07 | Create Product catalogue | Nitin
2013-04-07 | Create new Visiting card | Nitin
2013-04-07 | Get Vodafone number activated | Nitin
2013-04-07 | Chair and Furniture | Nitin
2013-04-07 | Drinking water setup | Nitin
2013-04-07 | Beautify old tables | Nitin
2013-04-07 | Get samples from Pawan 100 (end product) + 25 (PCB) for 5v solution 50 (end product) + 10 (PCB) for 8v solution Check Lantern body price | Nitin |  |  | 08/04: NJ: Called Pawan.He was busy. Mailed him on our requirement.
2013-04-07 | Identify Diode alternatives for SPV1040 | Srini + Sumit
2013-04-07 | Identify diode features for Zener and Schotkky | Srini + Sumit
2013-04-07 | Find and proocure Solar Panels | Nitin
2013-04-07 | Solar charger from different companies (with and without battery) and buy | Ajay/Nitin
2013-04-07 | Complete the Datasheet and product brief for Adaptor family | Sat/Mittal |  |  | Product Briefing Ready
| Update list of Suppliers/Vendors | Nitin
2013-04-13 | Super BOM for all Adaptor Family | Mittal
2013-04-14 | Identificaion and Procurement of Lantern Body ( option for mobile charging, AC charging, solar charging) | Nitin | 21/04/2013 | we will procure 100 samples
| Talk to SMF battery supplier - AMPTEK, 4.5Ah - 6v | Nitin | 21/04/2013 | we need to procure 100 pcs
| Talk to Solar Panel Supplier - 4-4.5Voc/1w panels | Nitin | 21/04/2013 | we need atleast 50 panels
| Identification for body of car battery Mobile charger | Nitin | 21/04/2013 | we would need atleast 100 pcs
| Crockery Setup in LAB | Nitin | 21/04/2013

## Medium
Entry Date | Tasks | Owner | Start Date | End Date | Priority | Status | Remarks
| PCB assembly - 1 piece and testing in lab | Sat |  |  | High
2013-01-08 | Create the final Schematic for Viper design | Srini/Sumit |  |  | High | Started
| Layout Software learning & 1040 gerber generation | Srini/Sumit |  |  | Medium
| Arrange catalog of connectors | Ajay |  |  | Medium
| 1040 PCB request to PCBpower | Sat |  |  | Medium
| Procurement for 1040 | Ajay |  |  | Medium
| Resource for testing boards | Ajay/Team |  |  | Medium
| Wave soldering/DIP solder m/c demo | Sat |  |  | Medium
| Study of wireless charger | Sumit/Srini |  |  | Medium
| Customer status document | Ajay/Nitin |  |  | Medium
| Document weaknesses of RE'd/tested designs | Sat |  |  | Medium
| Contact for assembly for pcb | Ajay/Team |  |  | Medium
| Create a soft copy for invoice papers | Ajay/Nitin |  |  | Medium | Ongoing
| Create Datasheet for Solar Lantern driver | Ajay |  |  | Medium | Ongoing
2013-01-15 | Prepare datasheet for Mobile Charger | Ajay |  |  | High | Started
| Update product/Corporate presentation | Ajay/Nitin |  |  | Medium | Ongoing
| Update Website with LED bulb & microcontroller details | Ajay/Nitin |  |  | Medium | Ongoing
2012-12-17 | Moxie USP | Ajay |  |  | Medium | Started
| Create 1 liner/caption for website | All |  |  | Medium | Yet to start
2013-01-15 | Consolidate various Transformers design and order sample from GSP | Sat |  |  | High | Started
2013-01-15 | Create Led driver board (isolated/non isolated config) | Sandeep/Sat |  |  | High | Yet to start
2013-01-08 | Sat's partnership name change | Nitin |  |  | High | Started
2013-01-15 | Define Roles and Responsibilities for everyone | All |  |  | High | Yet to start
HR

## Long Term
Entry Date | Category | Tasks | Owner | Start Date | End Date | Priority | Status | Remarks
| Marketing/Others | Prepare list of potential Customers via various sources | Nitin/All |  |  | Medium | Ongoing | Business repository placed
| Market Research | Check for BEE certification | Ajay |  |  | Medium | Yet to start
2012-12-17 | Market Research | Discuss with ERD and other competitors as a customer | Ajay |  |  | High | Yet to start
| Product - Solar Lantern | LED driver archietecture | Sandeep/Sumit |  |  | Medium | On-hold
| Product - Solar Lantern | LED study and purchase | Ajay |  |  | Medium | On-hold
| Product - Solar Lantern | Create online design document for Solar Lantern | Sandeep |  |  | Medium | On-hold
| Product - Solar Lantern | BOM calculation |  |  |  | Medium | On-hold
| Product - Solar Lantern | Identify customers/dealer |  |  |  | Medium | On-hold
| Product - Solar Lantern | Prototype + Test Design |  |  |  | Medium | On-hold
| Product - Solar Lantern | Quality Assurance |  |  |  | Medium | On-hold
| Product - Solar Mobile Charger | Create Design |  |  |  | High | Closed | ST design
| Product - Solar Mobile Charger | Source ST chip |  |  |  | High | Closed
| Product - Solar Mobile Charger | Study existing Designs |  |  |  | High | Yet to start
| Product - Solar Mobile Charger | Create Design and Design Reviews |  |  |  | Medium | Yet to start
| Product - Solar Mobile Charger | BOM calculation |  |  |  | Medium | Yet to start
| Product - Solar Mobile Charger | Identify customers/dealer |  |  |  | Medium | Yet to start
| Product - Solar Mobile Charger | Prototype + Test Design |  |  |  | Medium | Yet to start
| Product - Solar Mobile Charger | Quality Assurance |  |  |  | TBD | Yet to start
| Product - Solar Mobile Charger | Product documentation |  |  |  | Medium | Yet to start
| Product - Solar Mobile Charger | Liasing period with Supplier and Manufacturer |  |  |  | Medium | Yet to start
| Product - Mobile Charger | Study existing Designs | Technical Team |  |  | High | Closed
| Product - Mobile Charger | Create Design | Technical Team |  |  | High | Closed
2012-12-17 | Product - Mobile Charger | BOM for viper design and onsemi | Sat |  |  | High | Closed
2013-01-08 | Product - Mobile Charger | Transformer to be ordered with correct turn ratio | Mittal |  |  | High | Closed
| Product - Mobile Charger | Prototype + Test Design | Technical Team |  |  | High | Closed
| Product - Mobile Charger | Create PCB for 100 samples | Technical Team |  |  | High | Yet to start
| Product - Mobile Charger | Quality Assurance | Technical Team |  |  | Medium | Yet to start
| Product - Mobile Charger | Charger testing | All |  |  | Medium | Yet to start
2013-01-08 | Product - Mobile Charger | Final Cost calculation & Financial projection |  |  |  | High
2013-01-15 | Product - Mobile Charger | Identify customers/dealer | Ajay/Nitin |  |  | High | Started
2013-01-08 | Product - Mobile Charger | Check for current issues | All |  |  | High | Yet to start
2013-01-15 | Procurements | BOM costing from RadhaKrishna vendor | Ajay |  |  | High | Closed
2013-01-15 | Technical Research | Component Analysis - How to select a passive component | Sumit/Srini |  |  | High | Yet to start
| Long Term (6-12 Months) | Product feedback from Market |  |  |  | Low | Yet to start
| Long Term (6-12 Months) | Hire Marketing professional |  |  |  | Low | Yet to start
|  | Bring wooden rack to office | Sandeep |  |  |  | Closed
|  | Register Domain names online | Nitin |  |  |  | Closed
|  | Office stationaries/Wooden work/Electrical work in office | Nitin |  |  |  | Closed
|  | Register for EFY Magazine | Nitin |  |  |  | Closed
|  | Create Brand Name and Logo |  |  |  |  | Closed
|  | Create google group & Email a/c for firm |  |  |  |  | Closed
|  | Create Visiting Cards | Nitin |  |  |  | Closed
|  | Register Firm | Nitin |  |  |  | Closed
|  | Create Current Bank Account for Firm | Nitin |  |  |  | Closed
|  | Brand Name Marketing | Ajay/Nitin |  |  |  | Closed
|  | VAT Closure | Nitin |  |  | High | Closed
|  | Raise purchase order for BlueSky, MECO | Nitin |  |  | High | Closed
|  | Data sheet like we have for MSLD6D | Ajay/Nitin |  |  | High | Closed
|  | Workbench followup+shelf(glass) | Sat |  |  | Medium | Closed
|  | Additional equipment (power meter etc.) | Sat |  |  | Medium | Closed
|  | Collect Fujitsu samples after we gave LED load to them (lantern driver & bulb driver) | Nitin |  |  | Medium | Closed
|  | Discussion with Sahasra for led bulb, pcb lay out, assembly etc | Ajay |  |  | Medium | Closed